## Summary
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Ground Control — ESG Program Dashboard
Iniziative totali | 81
Progresso complessivo | 23.6%
On track (green) | 40
A rischio (amber) | 40
Bloccate (red) | 1
Prossimo gate | Q2 — 1 giorni
Three Horizons
H1 | 31 iniziative | 31.7%
H2 | 35 iniziative | 20.7%
H3 | 15 iniziative | 13.8%

## Iniziative
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
ID | Nome | Workstream | Pillar | Horizon | Lead | RAG | Progresso % | Deadline | Gate | Razionale
mcp-workday/api-discovery-map-whats-available | API Discovery — map what's available | mcp-workday | G | H2 | Francesco Mondora | AMBER | 0 | 2026-07-04 | Q3 | without knowing which endpoints are live and how auth works, everything else is guesswork
mcp-workday/auth-poc-prove-per-user-data-isolation | Auth PoC — prove per-user data isolation | mcp-workday | G | H1 | Francesco Mondora | AMBER | 0 | 2026-07-18 | Q3 | if employees can see each other's data, the project is dead on arrival
mcp-workday/mcp-prototype-3-core-tools | MCP Prototype — 3 core tools | mcp-workday | G | H3 | Francesco Mondora | AMBER | 0 | 2026-08-01 | Q3 | a working demo with real data is the best way to get buy-in and funding
mcp-workday/pilot-5-10-real-users | Pilot — 5-10 real users | mcp-workday | G | H2 | Francesco Mondora | AMBER | 0 | 2026-09-15 | Q3 | real feedback from real employees before scaling
reporting/nfd-2025 | NFD 2025 | reporting | G | H1 | Lucia Longoni | GREEN | 88 | 2026-07-31 | Q3 | disclosure obbligatoria — senza NFD niente compliance CSRD
reporting/ri-2025 | RI 2025 | reporting | G | H1 | Lucia Longoni | GREEN | 64 | 2026-07-31 | Q3 | relazione d'impatto — racconta cosa TeamSystem genera nel mondo
reporting/r1-standards-kpi | R1 Standards & KPI | reporting | G | H1 | Lucia Longoni | GREEN | 95 | 2026-05-31 | Q2 | standard e KPI interni per monitoraggio ESG — alimenta rating e compliance
reporting/rating-esg-novata-ecovadis | Rating ESG — Novata & Ecovadis | reporting | G | H2 | Lucia Longoni | GREEN | 15 | 2026-09-30 | Q3 | rating ESG esterni investor-facing — senza, niente benchmark e niente visibilita PE
reporting/deloitte-limited-assurance | Deloitte limited assurance | reporting | G | H1 | Francesco Mondora | AMBER | 0 | 2026-10-31 | YE | assurance di terza parte sulla NFD — requisito CSRD e aspettativa Board/PE
suppliers/piattaforma-supplier-valutazione-trasparenza | Piattaforma Supplier — Valutazione & Trasparenza | suppliers | G, S | H1 | Lucia Longoni | GREEN | 25 | 2026-09-30 | Q3 | senza valutazione strutturata, la due diligence fornitori resta manuale — modefinance + questionario self-improvement danno scala e trasparenza
suppliers/piattaforma-supplier-modulo-stakeholder-engagement | Piattaforma Supplier — Modulo Stakeholder Engagement | suppliers | G, S | H2 | Lucia Longoni | AMBER | 0 | 2026-10-31 | YE | seconda parte dell'integrazione — i segnali fornitore alimentano la DMA e il modulo SE della piattaforma
suppliers/top-10-supplier-interviews | Top 10 supplier interviews | suppliers | G, S | H2 | Lucia Longoni | AMBER | 0 | 2026-09-30 | Q3 | senza voce fornitori, la DMA manca una categoria critica — requisito ESRS S2 e G1 supply chain
suppliers/supplier-code-of-conduct-csddd-ready | Supplier Code of Conduct — CSDDD ready | suppliers | G, S | H1 | Lucia Longoni | AMBER | 0 | 2026-10-31 | YE | CSDDD non ancora cogente ma anticiparla e leva strategica — senza CoC, DNSH supply chain impossibile e Taxonomy alignment bloccato
suppliers/client-survey-s4 | Client survey S4 | suppliers | G, S | H1 | Lucia Longoni | AMBER | 0 | 2026-09-30 | Q3 | validazione esterna IRO G1 e S4 — senza voce clienti, materialita incompleta
suppliers/supplier-inclusion-green-procurement | Supplier Inclusion (green procurement) | suppliers | G, S | H2 | Lucia Longoni | AMBER | 0 | 2026-09-30 | Q3 | inclusione criteri green nella selezione fornitori — alimenta DNSH supply chain e CSDDD readiness
csr/project-management-setup-e-validazione | Project Management — setup e validazione | csr | S | H2 | Soljane Sabre | GREEN | 70 | 2026-06-30 | Q2 | senza team costituito, partner valutati e bisogni ETS validati, il bando parte su ipotesi — serve base solida
csr/project-design-disegno-bando-e-consultazione | Project Design — disegno bando e consultazione | csr | S | H1 | Soljane Sabre | GREEN | 30 | 2026-09-30 | Q3 | il bando deve essere co-progettato con i team e validato prima della pubblicazione — senza consultazione, manca legittimita
csr/pilot-launch-call-selezione-e-onboarding-ets | Pilot Launch — call, selezione e onboarding ETS | csr | S | H1 | Soljane Sabre | AMBER | 0 | 2026-12-31 | YE | il pilota valida il modello CSR con ETS reali — senza, resta teoria
ts-impact-platform/data-capture-modulo-operativo | Data Capture — modulo operativo | ts-impact-platform | G | H2 | Irene Brambilla | GREEN | 97 | 2026-06-30 | Q2 | senza data capture funzionante, la raccolta dati CSRD resta manuale per 52 entita
ts-impact-platform/fix-debito-tecnico-migrazione-postgrespgvector | Fix debito tecnico + migrazione Postgres/pgvector | ts-impact-platform | G | H1 | Irene Brambilla | AMBER | 0 | 2026-07-31 | Q3 | la piattaforma ha debito tecnico che blocca le evoluzioni — migrazione DB necessaria per search semantico e scalabilita
ts-impact-platform/formazione-data-capture-data-owners | Formazione Data Capture + data owners | ts-impact-platform | G | H2 | Irene Brambilla | AMBER | 0 | 2026-07-31 | Q3 | la piattaforma e' operativa ma i data owners devono saperla usare
ts-impact-platform/integrazione-workday-via-api | Integrazione Workday via API | ts-impact-platform | G | H2 | Irene Brambilla | AMBER | 0 | 2026-09-30 | Q3 | dati HR (headcount, turnover, diversity) devono fluire automaticamente dalla fonte — senza, raccolta manuale per 52 entita
ts-impact-platform/refactor-su-1platform | Refactor su 1Platform | ts-impact-platform | G | H2 | Irene Brambilla | AMBER | 0 | 2026-10-31 | YE | possibile migrazione dell'architettura sulla piattaforma unificata TeamSystem
ts-impact-platform/kpi-e-targets-in-piattaforma | KPI e Targets in piattaforma | ts-impact-platform | G | H2 | Irene Brambilla | AMBER | 0 | 2026-11-30 | YE | senza target in piattaforma, il monitoraggio ESG resta su Excel — serve per CSRD e Board
ts-impact-platform/dma-ma-doppia-materialita-acquisizioni | DMA M&A — doppia materialita acquisizioni | ts-impact-platform | G | H2 | Irene Brambilla | AMBER | 0 | 2026-12-31 | YE | ogni acquisizione cambia il perimetro CSRD — senza DMA M&A, le nuove entita non hanno IRO
inclusion/policy-inclusione-pubblicazione | Policy Inclusione — pubblicazione | inclusion | S | H3 | Stefania Pesola | AMBER | 15 | 2026-06-30 | Q2 | prerequisito per Inclusion Index, masterclass FNC, e disclosure ESRS S1
inclusion/inclusion-index-somministrazione-e-elaborazione | Inclusion Index — somministrazione e elaborazione | inclusion | S | H3 | Stefania Pesola | AMBER | 0 | 2026-09-30 | Q3 | misura la baseline inclusione — senza dati quantitativi, la policy resta dichiarazione di intenti e la masterclass non ha metriche
inclusion/masterclass-inclusione-fnc-erogazione | Masterclass Inclusione FNC — erogazione | inclusion | S | H3 | Stefania Pesola | AMBER | 0 | 2026-10-31 | YE | chiude il ciclo policy → misura → formazione — vincolata FNC (transizione ecologica, 75% frequenza, test finale)
operations/travel-catalog | Travel catalog | operations | E, S, G | H2 | Lucia Longoni | GREEN | 50 | 2026-12-31 | YE | catalogo emissioni travel per GHG Scope 3 — alimenta reporting e carbon strategy
operations/commute-catalog | Commute catalog | operations | E, S, G | H1 | Lucia Longoni | GREEN | 50 | 2026-12-31 | YE | catalogo emissioni commuting dipendenti per GHG Scope 3 — dati HR necessari
operations/environment-community | Environment Community | operations | E, S, G | H2 | Alice Simonetta | GREEN | 50 | 2026-12-31 | YE | community interna sensibilizzazione ambientale — engagement dipendenti e contenuti per RI
operations/prison-employment-vigevano | Prison Employment (Vigevano) | operations | E, S, G | H2 | Stefania Pesola | GREEN | 50 | 2026-12-31 | YE | progetto inclusione lavorativa detenuti — impatto sociale diretto, contenuto RI e S1
operations/gender-equality | Gender Equality | operations | E, S, G | H1 | Stefania Pesola | GREEN | 50 | 2026-12-31 | YE | monitoraggio e iniziative parita di genere — alimenta Inclusion Index e ESRS S1
operations/social-impact-non-profit | Social Impact Non Profit | operations | E, S, G | H1 | Alice Simonetta | GREEN | 50 | 2026-12-31 | YE | collaborazioni con non-profit per impatto sociale — contenuto RI e S3
operations/holding-the-space-pii | Holding the space (PII) | operations | E, S, G | H1 | Francesco Mondora | GREEN | 50 | 2026-12-31 | YE | presidio innovazione sociale interna — spazio sperimentale per iniziative ESG bottom-up
operations/public-funds-bandi | Public funds / bandi | operations | E, S, G | H2 | Alice Simonetta | GREEN | 50 | 2026-12-31 | YE | monitoraggio e partecipazione a bandi pubblici ESG — funding per iniziative
operations/admin-esg | Admin ESG | operations | E, S, G | H2 | Lucia Longoni | GREEN | 50 | 2026-12-31 | YE | overhead amministrativo team ESG — coordinamento, meeting, documentazione
operations/ground-control-sistema-operativo-esg | Ground Control — sistema operativo ESG | operations | E, S, G | H2 | Francesco Mondora | GREEN | 40 | 2026-12-31 | YE | il sistema che governa tutti gli stream — senza GC il team perde visibilita, coordinamento e tracciabilita
masterclass/preparazione-masterclass | Preparazione masterclass | masterclass | G | H3 | Francesco Mondora | GREEN | 26 | 2026-07-31 | Q3 | senza scaletta concordata e contenuti pronti, niente erogazione a settembre
masterclass/mcp-esg-per-dipendenti | MCP ESG per dipendenti | masterclass | G | H3 | Francesco Mondora | GREEN | 15 | 2026-09-30 | Q3 | il tool che rende la masterclass operativa — senza, resta teoria
masterclass/erogazione | Erogazione | masterclass | G | H2 | Francesco Mondora | AMBER | 0 | 2026-09-30 | Q3 | il momento in cui 4500 persone toccano ESG+AI con mano
taxonomy/mappatura-nace-prodotti-candidati | Mappatura NACE prodotti candidati | taxonomy | G | H1 | Anna Forlati | GREEN | 100 | 2026-04-30 | Q2 | identifica il perimetro di prodotti potenzialmente tassonomizzabili
taxonomy/classificazione-prodotti-con-product-success | Classificazione prodotti con Product Success | taxonomy | G | H1 | Anna Forlati | GREEN | 100 | 2026-05-31 | Q2 | senza classificazione, niente disclosure Taxonomy — serve allineare tutti i prodotti nel Product Success
taxonomy/dati-finanziari-per-prodotto | Dati finanziari per prodotto | taxonomy | G | H1 | Anna Forlati | AMBER | 20 | 2026-06-30 | Q2 | senza ricavi/capex/opex per prodotto classificato, la disclosure Taxonomy non ha KPI
taxonomy/agenti-esg-embedded-in-product-success | Agenti ESG embedded in Product Success | taxonomy | G | H3 | Anna Forlati | AMBER | 0 | 2026-09-30 | Q3 | scala la classificazione a tutti i prodotti TS — sistema agenti che collabora con Engineering Managers per embeddare ESG nel ciclo prodotto
taxonomy/dnsh-check-per-prodotto | DNSH check per prodotto | taxonomy | G | H1 | Anna Forlati | RED | 0 | 2026-09-30 | Q3 | requisito Taxonomy Regulation — senza DNSH nessun prodotto e aligned
taxonomy/validazione-board | Validazione Board | taxonomy | G | H2 | Francesco Mondora | AMBER | 0 | 2026-09-30 | Q3 | approvazione formale per disclosure pubblica
taxonomy/social-taxonomy-alignment | Social Taxonomy alignment | taxonomy | G | H1 | Anna Forlati | AMBER | 0 | 2027-06-30 |  | EU Social Taxonomy in consultazione — anticipare la classificazione prodotti su substantial contribution sociale allinea TeamSystem prima dei competitor
stakeholder-engagement/open-doors-s1-stakeholder-engagement-campaign | Open Doors — S1 stakeholder engagement campaign | stakeholder-engagement | S, G | H2 | Alice Simonetta | GREEN | 12.5 | 2026-09-16 | Q3 | without employee signals the DMA remains desk research
stakeholder-engagement/local-communities-s3 | Local communities S3 | stakeholder-engagement | S, G | H2 | Alice Simonetta | GREEN | 30 | 2026-07-31 | Q3 | external validation of IRO E3 and S3
stakeholder-engagement/engagement-agentico-dipendenti | Engagement agentico dipendenti | stakeholder-engagement | S, G | H3 | Francesco Mondora | GREEN | 30 | 2026-09-30 | Q3 | sistema di engagement via agenti ESG
stakeholder-engagement/sergenti-sistema-agentico-esg-team | Sergenti — sistema agentico ESG team | stakeholder-engagement | S, G | H3 | Francesco Mondora | GREEN | 50 | 2026-09-30 | Q3 | senza sistema, il 70% del processo resta manuale
stakeholder-engagement/impact-report-as-engagement-instrument | Impact Report as engagement instrument | stakeholder-engagement | S, G | H2 | Francesco Mondora | GREEN | 30 | 2026-07-31 | Q3 | the RI closes the loop DMA->disclosure->engagement->DMA_next
stakeholder-engagement/sbm-2-disclosure-draft | SBM-2 disclosure draft | stakeholder-engagement | S, G | H1 | Irene Brambilla | AMBER | 0 | 2026-10-31 | YE | mandatory ESRS disclosure
environment/bosco-teamsystem-audit-iso-14068-2-e-pefc | Bosco TeamSystem — audit ISO 14068-2 e PEFC | environment | E | H1 | Michele Romano Giamba | GREEN | 47.5 | 2026-07-31 | Q3 | senza audit completato, il dato ~1.480 tCO2/anno resta ex-ante — NFD E1-7 e RI Ambiente dipendono da dato aggiornato
environment/spritepinky-ghg-scope-3 | SpritePinky + GHG Scope 3 | environment | E | H3 | Michele Romano Giamba | GREEN | 11.7 | 2026-10-31 | YE | senza misurazione datacenter e Scope 3, la carbon strategy resta su stime — blocca carbon strategy, CarbonWallet, e compliance CSRD E1
environment/environment-policy-approvazione | Environment Policy — approvazione | environment | E | H2 | Francesco Mondora | GREEN | 23.3 | 2026-09-30 | Q3 | senza policy approvata, nessun target e vincolante e la Taxonomy non regge
environment/tnfd-leap-assessment | TNFD LEAP assessment | environment | E | H1 | Francesco Mondora | AMBER | 0 | 2026-09-30 | Q3 | disclosure natura e biodiversita — Bosco Valsesia e' il caso pilota, auditor si aspettano almeno un assessment qualitativo
environment/data-capture-piattaforma-esg-operativa | Data Capture piattaforma ESG — operativa | environment | E | H2 | Irene Brambilla | GREEN | 50 | 2026-07-31 | Q3 | governance raccolta dati ESG per tutte le subsidiary — senza, la CSRD multi-country resta manuale
environment/scope-12-split-per-subsidiary | Scope 1+2 split per subsidiary | environment | E | H2 | Michele Romano Giamba | AMBER | 0 | 2026-07-31 | Q3 | Siemens chiede a Microntel Net Zero Pathway — serve Scope 1+2 entity-level, non consolidato
environment/certificazione-iso-14068-1-carbon-neutrality | Certificazione ISO 14068-1 — Carbon Neutrality | environment | E | H2 | Michele Romano Giamba | AMBER | 0 | 2026-12-31 | YE | certificazione di terza parte sulla carbon neutrality — credibilita claim e compliance green claims directive
environment/botanical-garden-orto-botanico-teamsystem | Botanical Garden — Orto Botanico TeamSystem | environment | E | H2 | Francesco Vanossi | AMBER | 0 | 2026-12-31 | YE | progetto biodiversita e rigenerazione urbana — rafforza TNFD, employee engagement, e narrazione ESG
environment/rendicontazione-ghg-scope-3-hf-su-novata | Rendicontazione GHG Scope 3 — H&F su Novata | environment | E | H2 | Michele Romano Giamba | AMBER | 15 | 2026-06-30 | Q2 | Hellman & Friedman richiede rendicontazione GHG completa tramite piattaforma Novata — obbligo PE, visibilita investitore
carbon-wallet/metodologia-avoided-emissions-validazione | Metodologia Avoided Emissions — validazione | carbon-wallet | E, G | H1 | Anna Forlati | GREEN | 10 | 2026-07-31 | Q3 | senza metodologia validata, nessun prodotto puo dichiarare substantial contribution 8.2
carbon-wallet/engine-carbonwallet-bozza-v1 | Engine CarbonWallet — bozza v1 | carbon-wallet | E, G | H3 | Anna Forlati | AMBER | 0 | 2026-07-31 | Q3 | prima bozza funzionante del motore che traduce footprint in prodotto
carbon-wallet/engine-carbonwallet-v2-e-lancio | Engine CarbonWallet — v2 e lancio | carbon-wallet | E, G | H3 | Anna Forlati | AMBER | 0 | 2026-10-31 | YE | versione completa per 2M+ PMI — senza engine, la Taxonomy resta disclosure senza valore di mercato
product-success/toolkit-struttura-pilota | Toolkit struttura + pilota | product-success | E, G | H1 | Francesco Mondora | GREEN | 83.3 | 2026-07-31 | Q3 | validare il flusso end-to-end su un prodotto reale prima del rollout
product-success/rollout-10-prodotti-82 | Rollout 10 prodotti 8.2 | product-success | E, G | H3 | Anna Forlati | AMBER | 0 | 2026-10-31 | YE | copertura minima per disclosure Taxonomy e CarbonWallet pilota
program/ri-2025-pubblicazione-relazione-dimpatto | RI 2025 — pubblicazione Relazione d'Impatto | program | G | H1 | Lucia Longoni | AMBER | 30 | 2026-06-30 | Q2 | obbligo normativo Societa Benefit + base per CSRD FY2028
program/carbon-emission-strategy-environment-policy | Carbon Emission Strategy + Environment Policy | program | E | H2 | Francesco Mondora | GREEN | 30 | 2026-09-30 | Q3 | senza policy approvata, nessun target e vincolante e la Taxonomy non regge
program/carbonwallet-metodologia-ae-e-pilota-engine | CarbonWallet — metodologia AE e pilota engine | program | E, G | H3 | Anna Forlati | GREEN | 30 | 2026-09-30 | Q3 | traduce footprint in prodotto per 2M+ PMI e calcola substantial contribution 8.2 — senza, la Taxonomy resta disclosure senza valore di mercato
program/supplier-code-of-conduct-csddd-ready | Supplier Code of Conduct — CSDDD ready | program | G | H1 | Lucia Longoni | AMBER | 0 | 2026-10-31 | YE | CSDDD non ancora cogente ma anticiparla e leva strategica — senza CoC, DNSH supply chain impossibile
program/board-esg-settembre-green-taxonomy-carbon-strategy | Board ESG settembre — Green Taxonomy + Carbon Strategy | program | G | H2 | Francesco Mondora | AMBER | 0 | 2026-09-30 | Q3 | approvazione formale Board per disclosure Taxonomy pubblica e carbon strategy — senza, tutto resta interno
program/cultura-e-formazione-masterclass-esgai-inclusione | Cultura e Formazione — Masterclass ESG+AI + Inclusione | program | S, G | H3 | Francesco Mondora | GREEN | 30 | 2026-10-31 | YE | proof che ground-control funziona come metodo — se 4500 persone lo usano, diventa standard. Include masterclass ESG+AI, policy inclusione, e formazione FNC.
program/stakeholder-engagement-dma-multi-category | Stakeholder Engagement — DMA multi-category | program | S, G | H2 | Francesco Mondora | GREEN | 30 | 2026-09-30 | Q3 | senza stakeholder engagement, la DMA non ha legittimita esterna — requisito ESRS 1 e aspettativa auditor
program/dma-2026-avvio-doppia-materialita-internazionale | DMA 2026 — avvio doppia materialita internazionale | program | G | H2 | Francesco Mondora | AMBER | 0 | 2026-09-30 | Q3 | senza DMA scope internazionale, la CSRD Group FY2028 parte in ritardo di 1 anno
program/green-ai-sostenibilita-computazionale | Green AI — sostenibilita computazionale | program | E, G | H1 | Francesco Mondora | GREEN | 30 | 2026-12-31 | YE | misurare e ridurre impatto ambientale AI/ML — EVP product, differenziatore per clienti e PE
program/digital-impact-on-products-misurazione-impatto-digitale | Digital Impact on products — misurazione impatto digitale | program | E, S, G | H1 | Anna Forlati | GREEN | 30 | 2026-12-31 | YE | quantificare l'impatto ESG dei prodotti TeamSystem sui 2M+ clienti — EVP product e narrazione RI
program/budget-fy2026-approvazione | Budget FY2026 — approvazione | program | G | H1 | Francesco Mondora | GREEN | 30 | 2026-07-31 | Q3 | senza budget approvato, ogni RDA richiede approvazione ad hoc — rallenta tutto e genera incertezza sui fornitori
program/evento-hf-24-giugno-francesco-speaker | Evento H&F 24 giugno — Francesco speaker | program | G | H2 | Francesco Mondora | AMBER | 30 | 2026-06-24 | Q2 | visibilita ESG verso Hellman & Friedman — il PE owner vuole vedere progressi concreti, non slide
program/processo-rda-digitalizzazione | Processo RDA — digitalizzazione | program | G | H1 | Lucia Longoni | AMBER | 0 | 2026-09-30 | Q3 | tracking manuale RDA su email e foglio Excel — errori, ritardi, nessuna visibilita real-time

## Workstream
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
ID | Nome | Pillar | Lead | Livello | RAG | Progresso % | Strategy | Structure | Systems | Shared Values | Skills | Style | Staff
mcp-workday | MCP Workday | G | Francesco Mondora | L1 | AMBER | 0 | 10 | 10 | 4 | 6 | 10 | 5 | 10
reporting | Reporting ESG 2025 | G | Lucia Longoni | L2 | AMBER | 52.4 | 10 | 10 | 7 | 6 | 8 | 8 | 10
suppliers | Supplier Engagement & Qualification | G, S | Lucia Longoni | L2 | AMBER | 4.2 | 10 | 10 | 7 | 8 | 4 | 5 | 10
csr | Corporate Social Responsibility | S | Soljane Sabre | L1 | AMBER | 33.3 | 10 | 10 | 4 | 6 | 4 | 5 | 10
ts-impact-platform | TeamSystem Impact Platform | G | Irene Brambilla | L2 | AMBER | 13.9 | 10 | 10 | 7 | 6 | 4 | 5 | 10
inclusion | Inclusion & Diversity | S | Stefania Pesola | L1 | AMBER | 5 | 10 | 10 | 4 | 6 | 4 | 8 | 10
operations | Operations & BAU | E, S, G | Lucia Longoni | L2 | GREEN | 49 | 10 | 10 | 7 | 10 | 4 | 5 | 8
masterclass | ESG Masterclass | G | Francesco Mondora | L1 | AMBER | 13.7 | 10 | 10 | 4 | 6 | 7 | 5 | 10
taxonomy | Green Taxonomy | G | Anna Forlati | L1 | RED | 31.4 | 10 | 10 | 4 | 6 | 7 | 8 | 10
stakeholder-engagement | Stakeholder Engagement DMA 2026 | S, G | Francesco Mondora | L2 | AMBER | 25.4 | 10 | 10 | 7 | 8 | 10 | 5 | 8
environment | Environment & Climate | E | Michele Romano Giamba | L1 | AMBER | 16.4 | 10 | 10 | 4 | 6 | 4 | 8 | 10
carbon-wallet | CarbonWallet — Portafoglio Carbonio | E, G | Anna Forlati | L1 | AMBER | 3.3 | 10 | 10 | 4 | 8 | 4 | 8 | 10
product-success | Product Success Agents | E, G | Francesco Mondora | L1 | AMBER | 41.6 | 10 | 10 | 4 | 8 | 4 | 5 | 6

## People
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Nome | Ruolo | Workstream | Lead | Co-owner | Spec | Weight | Focus | Top Stream | Concentrazione | Competenze
Francesco Mondora | decides | mcp-workday, reporting, suppliers, csr, ts-impact-platform, inclusion, operations, masterclass, taxonomy, stakeholder-engagement, environment, carbon-wallet, product-success, program | 25 | 10 | 7 | 102 | distributed | program | 24% | vision, architecture, policy, ESG strategy, carbon, taxonomy, masterclass
Lucia Longoni | orchestrates | reporting, suppliers, ts-impact-platform, operations, masterclass, stakeholder-engagement, environment, program | 16 | 3 | 3 | 57 | distributed | suppliers | 32% | data pipeline, ESRS mapping, priority triage, reporting workflow, supplier engagement
Anna Forlati | reviews | reporting, suppliers, csr, ts-impact-platform, masterclass, taxonomy, stakeholder-engagement, environment, carbon-wallet, product-success, program | 12 | 0 | 1 | 37 | distributed | taxonomy | 49% | observation, review, quality check
Irene Brambilla | validates | reporting, ts-impact-platform, masterclass, stakeholder-engagement, program | 9 | 0 | 0 | 27 | focused | ts-impact-platform | 78% | ESRS mapping, data validation, precise execution
Alice Simonetta | builds | csr, operations, masterclass, stakeholder-engagement, environment, program | 5 | 1 | 3 | 20 | distributed | operations | 45% | admin, routine tasks
Michele Romano Giamba | builds | operations, environment, carbon-wallet, program | 5 | 0 | 1 | 16 | focused | environment | 94% | carbon accounting, datacenter, environment, forests, ISO 14068
Stefania Pesola | builds | csr, inclusion, operations, stakeholder-engagement, program | 5 | 0 | 0 | 15 | distributed | inclusion | 60% | inclusion, CSR, social impact, prison employment
Soljane Sabre | builds | csr, program | 3 | 0 | 0 | 9 | focused | csr | 100% | CSR, non-profit engagement, social impact, bandi
Donatella Isaia | decides | inclusion, program | 0 | 3 | 1 | 7 | available | inclusion | 100% | direction, approval, people strategy
Luca Montecchiani | builds | carbon-wallet, program | 0 | 0 | 1 | 1 | available | carbon-wallet | 100% | field operations

## Rischi
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Iniziativa | Workstream | Rischio | Impatto | Probabilita | Owner | Mitigazione
API Discovery — map what's available | mcp-workday | API Discovery — map what's available: 5 days to deadline, 0.0% done | high | medium | Francesco Mondora | Accelerate or descope
Auth PoC — prove per-user data isolation | mcp-workday | Auth PoC — prove per-user data isolation: 19 days to deadline, 0.0% done | high | medium | Francesco Mondora | Accelerate or descope
Policy Inclusione — pubblicazione | inclusion | Policy Inclusione — pubblicazione: 1 days to deadline, 15.0% done | high | medium | Stefania Pesola | Accelerate or descope
Dati finanziari per prodotto | taxonomy | Dati finanziari per prodotto: 1 days to deadline, 20.0% done | high | medium | Anna Forlati | Accelerate or descope
DNSH check per prodotto | taxonomy | DNSH check per prodotto is blocked | high | high | Anna Forlati | Unblock dependencies
Rendicontazione GHG Scope 3 — H&F su Novata | environment | Rendicontazione GHG Scope 3 — H&F su Novata: 1 days to deadline, 15.0% done | high | medium | Michele Romano Giamba | Accelerate or descope
RI 2025 — pubblicazione Relazione d'Impatto | program | RI 2025 — pubblicazione Relazione d'Impatto: 1 days to deadline, 30.0% done | high | medium | Lucia Longoni | Accelerate or descope
Evento H&F 24 giugno — Francesco speaker | program | Evento H&F 24 giugno — Francesco speaker: -5 days to deadline, 30.0% done | high | medium | Francesco Mondora | Accelerate or descope

## Decisioni
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Iniziativa | Workstream | Decisione | Owner | Scadenza | Stato
API Discovery — map what's available | mcp-workday | API Discovery — map what's available — gate Q3 approval | Francesco Mondora | 2026-07-04 | pending
Auth PoC — prove per-user data isolation | mcp-workday | Auth PoC — prove per-user data isolation — gate Q3 approval | Francesco Mondora | 2026-07-18 | pending
MCP Prototype — 3 core tools | mcp-workday | MCP Prototype — 3 core tools — gate Q3 approval | Francesco Mondora | 2026-08-01 | pending
Pilot — 5-10 real users | mcp-workday | Pilot — 5-10 real users — gate Q3 approval | Francesco Mondora | 2026-09-15 | pending
Deloitte limited assurance | reporting | Deloitte limited assurance — gate YE approval | Francesco Mondora | 2026-10-31 | pending
Piattaforma Supplier — Modulo Stakeholder Engagement | suppliers | Piattaforma Supplier — Modulo Stakeholder Engagement — gate YE approval | Lucia Longoni | 2026-10-31 | pending
Top 10 supplier interviews | suppliers | Top 10 supplier interviews — gate Q3 approval | Lucia Longoni | 2026-09-30 | pending
Supplier Code of Conduct — CSDDD ready | suppliers | Supplier Code of Conduct — CSDDD ready — gate YE approval | Lucia Longoni | 2026-10-31 | pending
Client survey S4 | suppliers | Client survey S4 — gate Q3 approval | Lucia Longoni | 2026-09-30 | pending
Supplier Inclusion (green procurement) | suppliers | Supplier Inclusion (green procurement) — gate Q3 approval | Lucia Longoni | 2026-09-30 | pending
Pilot Launch — call, selezione e onboarding ETS | csr | Pilot Launch — call, selezione e onboarding ETS — gate YE approval | Soljane Sabre | 2026-12-31 | pending
Fix debito tecnico + migrazione Postgres/pgvector | ts-impact-platform | Fix debito tecnico + migrazione Postgres/pgvector — gate Q3 approval | Irene Brambilla | 2026-07-31 | pending
Formazione Data Capture + data owners | ts-impact-platform | Formazione Data Capture + data owners — gate Q3 approval | Irene Brambilla | 2026-07-31 | pending
Integrazione Workday via API | ts-impact-platform | Integrazione Workday via API — gate Q3 approval | Irene Brambilla | 2026-09-30 | pending
Refactor su 1Platform | ts-impact-platform | Refactor su 1Platform — gate YE approval | Irene Brambilla | 2026-10-31 | pending
KPI e Targets in piattaforma | ts-impact-platform | KPI e Targets in piattaforma — gate YE approval | Irene Brambilla | 2026-11-30 | pending
DMA M&A — doppia materialita acquisizioni | ts-impact-platform | DMA M&A — doppia materialita acquisizioni — gate YE approval | Irene Brambilla | 2026-12-31 | pending
Policy Inclusione — pubblicazione | inclusion | Policy Inclusione — pubblicazione — gate Q2 approval | Stefania Pesola | 2026-06-30 | pending
Inclusion Index — somministrazione e elaborazione | inclusion | Inclusion Index — somministrazione e elaborazione — gate Q3 approval | Stefania Pesola | 2026-09-30 | pending
Masterclass Inclusione FNC — erogazione | inclusion | Masterclass Inclusione FNC — erogazione — gate YE approval | Stefania Pesola | 2026-10-31 | pending
Erogazione | masterclass | Erogazione — gate Q3 approval | Francesco Mondora | 2026-09-30 | pending
Dati finanziari per prodotto | taxonomy | Dati finanziari per prodotto — gate Q2 approval | Anna Forlati | 2026-06-30 | pending
Agenti ESG embedded in Product Success | taxonomy | Agenti ESG embedded in Product Success — gate Q3 approval | Anna Forlati | 2026-09-30 | pending
DNSH check per prodotto | taxonomy | DNSH check per prodotto — gate Q3 approval | Anna Forlati | 2026-09-30 | pending
Validazione Board | taxonomy | Validazione Board — gate Q3 approval | Francesco Mondora | 2026-09-30 | pending
SBM-2 disclosure draft | stakeholder-engagement | SBM-2 disclosure draft — gate YE approval | Irene Brambilla | 2026-10-31 | pending
SpritePinky + GHG Scope 3 | environment | Scegliere partner per validazione calcoli SpritePinky (ERM rimossa) | Francesco Mondora |  | pending
TNFD LEAP assessment | environment | TNFD LEAP assessment — gate Q3 approval | Francesco Mondora | 2026-09-30 | pending
Scope 1+2 split per subsidiary | environment | Scope 1+2 split per subsidiary — gate Q3 approval | Michele Romano Giamba | 2026-07-31 | pending
Certificazione ISO 14068-1 — Carbon Neutrality | environment | Certificazione ISO 14068-1 — Carbon Neutrality — gate YE approval | Michele Romano Giamba | 2026-12-31 | pending
Botanical Garden — Orto Botanico TeamSystem | environment | Botanical Garden — Orto Botanico TeamSystem — gate YE approval | Francesco Vanossi | 2026-12-31 | pending
Rendicontazione GHG Scope 3 — H&F su Novata | environment | Rendicontazione GHG Scope 3 — H&F su Novata — gate Q2 approval | Michele Romano Giamba | 2026-06-30 | pending
Metodologia Avoided Emissions — validazione | carbon-wallet | Validazione esterna AE + CarbonWallet | Francesco Mondora |  | decided
Engine CarbonWallet — bozza v1 | carbon-wallet | Engine CarbonWallet — bozza v1 — gate Q3 approval | Anna Forlati | 2026-07-31 | pending
Engine CarbonWallet — v2 e lancio | carbon-wallet | Engine CarbonWallet — v2 e lancio — gate YE approval | Anna Forlati | 2026-10-31 | pending
Rollout 10 prodotti 8.2 | product-success | Rollout 10 prodotti 8.2 — gate YE approval | Anna Forlati | 2026-10-31 | pending
RI 2025 — pubblicazione Relazione d'Impatto | program | RI 2025 — pubblicazione Relazione d'Impatto — gate Q2 approval | Lucia Longoni | 2026-06-30 | pending
Supplier Code of Conduct — CSDDD ready | program | Supplier Code of Conduct — CSDDD ready — gate YE approval | Lucia Longoni | 2026-10-31 | pending
Board ESG settembre — Green Taxonomy + Carbon Strategy | program | Board ESG settembre — Green Taxonomy + Carbon Strategy — gate Q3 approval | Francesco Mondora | 2026-09-30 | pending
DMA 2026 — avvio doppia materialita internazionale | program | DMA 2026 — avvio doppia materialita internazionale — gate Q3 approval | Francesco Mondora | 2026-09-30 | pending
Evento H&F 24 giugno — Francesco speaker | program | Evento H&F 24 giugno — Francesco speaker — gate Q2 approval | Francesco Mondora | 2026-06-24 | pending
Processo RDA — digitalizzazione | program | Processo RDA — digitalizzazione — gate Q3 approval | Lucia Longoni | 2026-09-30 | pending

## Dipendenze
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Da | A | Tipo | Descrizione
mcp-workday/api-discovery-map-whats-available | mcp-workday/auth-poc-prove-per-user-data-isolation | depends_on | sandbox + oauth client + endpoint list
mcp-workday/auth-poc-prove-per-user-data-isolation | mcp-workday/mcp-prototype-3-core-tools | depends_on | validated auth flow
mcp-workday/mcp-prototype-3-core-tools | mcp-workday/pilot-5-10-real-users | depends_on | working tools with auth
carbon | reporting/nfd-2025 | depends_on | dati GHG Scope 1/2/3
carbon | reporting/ri-2025 | depends_on | dati GHG Scope 1/2/3
reporting/nfd-2025 | reporting/deloitte-limited-assurance | depends_on | NFD completata e impaginata
reporting/deloitte-limited-assurance | ground-control | blocks | CSRD compliance — assurance e' requisito
ts-impact-platform | suppliers/piattaforma-supplier-valutazione-trasparenza | depends_on | piattaforma Impact come base per il modulo
suppliers/piattaforma-supplier-valutazione-trasparenza | suppliers/top-10-supplier-interviews | blocks | il modulo da contesto strutturato alle interviste
suppliers/piattaforma-supplier-valutazione-trasparenza | suppliers/supplier-code-of-conduct-csddd-ready | blocks | il pilot fornisce evidenza per informare il CoC
suppliers/piattaforma-supplier-valutazione-trasparenza | suppliers/piattaforma-supplier-modulo-stakeholder-engagement | depends_on | serve il modulo valutazione operativo
suppliers/piattaforma-supplier-modulo-stakeholder-engagement | stakeholder-engagement/sbm-2-disclosure-draft | blocks | segnali fornitori per consolidamento SBM-2
suppliers/piattaforma-supplier-valutazione-trasparenza | suppliers/top-10-supplier-interviews | depends_on | pilot completato, dati modefinance disponibili per le interviste
suppliers/piattaforma-supplier-valutazione-trasparenza | suppliers/supplier-code-of-conduct-csddd-ready | depends_on | evidenza dal pilot informa i requisiti del CoC
suppliers/piattaforma-supplier-valutazione-trasparenza | suppliers/supplier-inclusion-green-procurement | depends_on | piattaforma operativa come base per filtri green
suppliers/supplier-code-of-conduct-csddd-ready | suppliers/supplier-inclusion-green-procurement | depends_on | CoC definisce i requisiti ESG fornitori
csr/project-management-setup-e-validazione | csr/project-design-disegno-bando-e-consultazione | blocks | senza bisogni validati, il disegno del bando e cieco
csr/project-management-setup-e-validazione | csr/project-design-disegno-bando-e-consultazione | depends_on | bisogni ETS e team pronti
csr/project-design-disegno-bando-e-consultazione | csr/pilot-launch-call-selezione-e-onboarding-ets | blocks | senza bando finalizzato, niente apertura call
csr/project-design-disegno-bando-e-consultazione | csr/pilot-launch-call-selezione-e-onboarding-ets | depends_on | bando finalizzato e approvato
csr/pilot-launch-call-selezione-e-onboarding-ets | reporting | blocks | KPI impatto sociale per NFD S1/S3 e RI
csr/pilot-launch-call-selezione-e-onboarding-ets | stakeholder-engagement/sbm-2-disclosure-draft | blocks | evidenza impatto CSR per categoria community/S3
ts-impact-platform/data-capture-modulo-operativo | ts-impact-platform/formazione-data-capture-data-owners | blocks | modulo deve essere completo prima della formazione
ts-impact-platform/fix-debito-tecnico-migrazione-postgrespgvector | ts-impact-platform/integrazione-workday | blocks | senza DB stabile, le integrazioni non reggono
ts-impact-platform/fix-debito-tecnico-migrazione-postgrespgvector | ts-impact-platform/integrazione-workday-via-api | depends_on | DB stabile prima di aggiungere integrazioni
ts-impact-platform/integrazione-workday-via-api | ts-impact-platform/kpi-e-targets-in-piattaforma | depends_on | dati reali necessari per popolare KPI
social | inclusion/policy-inclusione-pubblicazione | depends_on | Policy Diversita e Inclusione 2024 come base
inclusion/policy-inclusione-pubblicazione | inclusion/inclusion-index-somministrazione-e-elaborazione | blocks | senza policy pubblicata, il questionario non ha framework
inclusion/policy-inclusione-pubblicazione | inclusion/masterclass-inclusione-fnc-erogazione | blocks | senza policy, la masterclass non ha framework
inclusion/policy-inclusione-pubblicazione | reporting | blocks | ESRS S1 disclosure — claim CLM-A-059 da risolvere
inclusion/policy-inclusione-pubblicazione | inclusion/inclusion-index-somministrazione-e-elaborazione | depends_on | senza policy pubblicata, il questionario non ha framework di riferimento
inclusion/inclusion-index-somministrazione-e-elaborazione | inclusion/masterclass-inclusione-fnc-erogazione | blocks | senza dati Index, la masterclass non ha metriche ne' baseline
inclusion/inclusion-index-somministrazione-e-elaborazione | reporting | blocks | ESRS S1 datapoint su inclusione
inclusion/policy-inclusione-pubblicazione | inclusion/masterclass-inclusione-fnc-erogazione | depends_on | senza policy, la masterclass non ha framework
inclusion/inclusion-index-somministrazione-e-elaborazione | inclusion/masterclass-inclusione-fnc-erogazione | depends_on | senza dati Index, la masterclass non ha metriche ne' baseline
environment/spritepinky-ghg-scope-3 | operations/commute-catalog | depends_on | metodologia Scope 3 per calcolo emissioni commute
inclusion/policy-inclusione-pubblicazione | operations/gender-equality | depends_on | policy come framework per iniziative gender
csr | operations/social-impact-non-profit | depends_on | metodologia CSR per selezione e valutazione non-profit
reporting | operations/ground-control-sistema-operativo-esg | depends_on | dati per dashboard e trends
taxonomy | operations/ground-control-sistema-operativo-esg | depends_on | dati per dashboard e trends
taxonomy/classificazione-prodotti-con-product-success | taxonomy/dati-finanziari-per-prodotto | blocks | senza classificazione, non si sa a quali prodotti associare i ricavi
taxonomy/classificazione-prodotti-con-product-success | reporting | blocks | classificazione prodotti per NFD e RI
taxonomy/classificazione-prodotti-con-product-success | taxonomy/dati-finanziari-per-prodotto | depends_on | serve sapere quali prodotti sono eligible/aligned
taxonomy/dati-finanziari-per-prodotto | reporting | blocks | KPI ricavi/capex/opex per NFD e RI
taxonomy/dati-finanziari-per-prodotto | taxonomy/validazione-board | blocks | senza KPI, niente presentazione Board
taxonomy/classificazione-prodotti-con-product-success | taxonomy/agenti-esg-embedded-in-product-success | depends_on | la classificazione iniziale e' il training data per gli agenti
compliance | taxonomy/dnsh-check-per-prodotto | depends_on | policy procurement
taxonomy/dnsh-check-per-prodotto | reporting | blocks | disclosure Taxonomy completa
taxonomy | taxonomy/validazione-board | depends_on | DNSH check completato
taxonomy/validazione-board | taxonomy/social-taxonomy-alignment | depends_on | Green Taxonomy completata prima di iniziare Social
environment/bosco-teamsystem-audit-iso-14068-2-e-pefc | reporting | blocks | dato assorbimento per E1-7 e RI sezione Ambiente
environment | environment/spritepinky-ghg-scope-3 | depends_on | fee GreenPixie 10k approvata
environment/spritepinky-ghg-scope-3 | program/carbon-emission-strategy-environment-policy | blocks | senza dati datacenter reali, la carbon strategy resta su stime
environment/spritepinky-ghg-scope-3 | carbon-wallet | blocks | SpritePinky alloca emissioni per cliente — input footprint CarbonWallet
environment/environment-policy-approvazione | ground-control/board-esg-settembre | blocks | carbon strategy e' meta della presentazione Board
environment/environment-policy-approvazione | taxonomy | blocks | environment policy necessaria per contesto DNSH
environment/spritepinky-misurazione-emissioni-datacenter | environment/tnfd-leap-assessment | depends_on | validazione calcoli necessaria prima di assessment biodiversita
environment/data-capture-piattaforma-esg-operativa | ts-impact-platform/csrd-data-collection-pipeline | blocks | data capture e' il componente operativo della pipeline
environment/spritepinky-misurazione-emissioni-datacenter | environment/certificazione-iso-14068-1-carbon-neutrality | depends_on | dati emissioni reali necessari per quantificazione carbon neutrality
environment/bosco-teamsystem-audit-pefc-e-aggiornamento-dati | environment/certificazione-iso-14068-1-carbon-neutrality | depends_on | dato assorbimento verificato necessario per bilancio carbon neutrality
environment/rendicontazione-ghg-scope-3-hf-su-novata | ground-control/evento-hf-24-giugno | blocks | dati GHG necessari per la presentazione Francesco
environment/spritepinky-misurazione-emissioni-datacenter | carbon-wallet/metodologia-avoided-emissions-validazione | depends_on | footprint reale per prodotto/transazione
carbon-wallet/metodologia-avoided-emissions-validazione | taxonomy | blocks | AE methodology necessaria per classificare prodotti come 8.2 aligned
carbon-wallet/metodologia-avoided-emissions-validazione | carbon-wallet/engine-carbonwallet-bozza-v1 | depends_on | senza AE validate, niente calcolo alignment
environment/spritepinky-misurazione-emissioni-datacenter | carbon-wallet/engine-carbonwallet-bozza-v1 | depends_on | footprint per allocazione a cliente
carbon-wallet/engine-carbonwallet-bozza-v1 | carbon-wallet/engine-carbonwallet-v2-e-lancio | depends_on | feedback dalla prima bozza
carbon-wallet/engine-carbonwallet-v2-e-lancio | ground-control/board-esg-settembre | blocks | CarbonWallet come caso d'uso nella presentazione Board
taxonomy | product-success/toolkit-struttura-pilota | depends_on | emission factors per le 6 famiglie (gia disponibili)
carbon | product-success/toolkit-struttura-pilota | depends_on | architettura CarbonWallet Engine (gia disponibile)
product-success | product-success/rollout-10-prodotti-82 | depends_on | pilota completato (milestone 1)
reporting/ri-2025 | program/ri-2025-pubblicazione-relazione-dimpatto | depends_on | contenuto narrativo + dati + impaginazione
program/ri-2025-pubblicazione-relazione-dimpatto | stakeholder-engagement/impact-report-as-engagement-instrument | blocks | senza RI pubblicata, niente distribuzione a stakeholder
environment | program/carbon-emission-strategy-environment-policy | depends_on | SpritePinky location-based + ISO 14068/2 foreste
program/carbon-emission-strategy-environment-policy | taxonomy/validazione-board | blocks | carbon strategy e' metà della presentazione Board
environment/spritepinky-misurazione-emissioni-datacenter | program/carbonwallet-metodologia-ae-e-pilota-engine | depends_on | footprint reale per prodotto/transazione
taxonomy | program/carbonwallet-metodologia-ae-e-pilota-engine | depends_on | classificazione prodotti 8.1/8.2
program/carbonwallet-metodologia-ae-e-pilota-engine | taxonomy | blocks | avoided emissions per substantial contribution 8.2
program/carbonwallet-metodologia-ae-e-pilota-engine | reporting | blocks | KPI Turnover/CapEx/OpEx per NFD Taxonomy section
program/carbonwallet-metodologia-ae-e-pilota-engine | ground-control/board-esg-settembre | blocks | CarbonWallet come caso d'uso Board
program/supplier-code-of-conduct-csddd-ready | taxonomy/dnsh-check-per-prodotto | blocks | Policy procurement DNSH richiede code of conduct approvato
taxonomy/validazione-board | program/board-esg-settembre-green-taxonomy-carbon-strategy | depends_on | deck con classificazione + ricavi + DNSH
environment | program/board-esg-settembre-green-taxonomy-carbon-strategy | depends_on | carbon emission strategy approvata CE
masterclass/preparazione-masterclass | program/cultura-e-formazione-masterclass-esgai-inclusione | depends_on | scaletta + contenuti pronti
masterclass/mcp-esg-per-dipendenti | program/cultura-e-formazione-masterclass-esgai-inclusione | depends_on | agenti ESG integrati con le piattaforme
inclusion/policy-inclusione-pubblicazione | program/cultura-e-formazione-masterclass-esgai-inclusione | depends_on | policy prerequisito per masterclass FNC
stakeholder-engagement/open-doors-s1-stakeholder-engagement-campaign | program/stakeholder-engagement-dma-multi-category | depends_on | 8 stop completati con survey DMA
stakeholder-engagement/engagement-agentico-dipendenti | program/stakeholder-engagement-dma-multi-category | depends_on | sistema agenti ESG operativo per 4500 dipendenti
program/stakeholder-engagement-dma-multi-category | stakeholder-engagement/sbm-2-disclosure-draft | blocks | senza dati consolidati, niente SBM-2
reporting/ri-2025 | program/dma-2026-avvio-doppia-materialita-internazionale | depends_on | RI pubblicata come baseline
stakeholder-engagement/sbm-2-disclosure-draft | program/dma-2026-avvio-doppia-materialita-internazionale | depends_on | matrice IRO aggiornata con score stakeholder
environment/spritepinky-ghg-scope-3 | program/green-ai-sostenibilita-computazionale | depends_on | dati emissioni datacenter per calcolo footprint AI
taxonomy | program/digital-impact-on-products-misurazione-impatto-digitale | depends_on | classificazione prodotti per mappare impatto
carbon-wallet | program/digital-impact-on-products-misurazione-impatto-digitale | depends_on | CarbonWallet come caso d'uso impatto digitale

## Autonomia
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Stream | Tier Attuale | Knowledge Infra | Workflow Std | Agent Coverage | Handoff Friction | Maturity Score | Tier Target | Rischio Inazione | Agenti | Blocchi
Operations & BAU | L2 | 4.8 | 2 | 0 | 5 | 2.9 | L1 | 6 | 0 | Agent coverage insufficient for L3: need 5+ agents with 3+ categories Too many cross-stream handoffs: reduce external dependencies or automate handoffs Knowledge graph incomplete: need done_when, why, depends_on on all milestones
Environment & Climate | L1 | 7.6 | 10 | 0 | 4 | 5.6 | L2 | 6 | 0 | No agents: need at least 2-3 agents for 90% automation Agent coverage insufficient for L3: need 5+ agents with 3+ categories Too many cross-stream handoffs: reduce external dependencies or automate handoffs
Green Taxonomy | L1 | 7.7 | 10 | 10 | 5 | 8.3 | L3 | 4.8 | 6 | Too many cross-stream handoffs: reduce external dependencies or automate handoffs
CarbonWallet — Portafoglio Carbonio | L1 | 8 | 10 | 0 | 5 | 5.9 | L2 | 4.5 | 0 | No agents: need at least 2-3 agents for 90% automation Agent coverage insufficient for L3: need 5+ agents with 3+ categories Too many cross-stream handoffs: reduce external dependencies or automate handoffs
Reporting ESG 2025 | L2 | 7.2 | 10 | 10 | 5 | 8.2 | L3 | 4.3 | 11 | Too many cross-stream handoffs: reduce external dependencies or automate handoffs
Supplier Engagement & Qualification | L2 | 7.7 | 8 | 0 | 7 | 5.7 | L2 | 4.2 | 0 | Agent coverage insufficient for L3: need 5+ agents with 3+ categories
Inclusion & Diversity | L1 | 8 | 10 | 0 | 5 | 5.9 | L2 | 3.9 | 0 | No agents: need at least 2-3 agents for 90% automation Agent coverage insufficient for L3: need 5+ agents with 3+ categories Too many cross-stream handoffs: reduce external dependencies or automate handoffs
TeamSystem Impact Platform | L2 | 7.1 | 8 | 0 | 7 | 5.5 | L2 | 3.6 | 0 | Agent coverage insufficient for L3: need 5+ agents with 3+ categories
Stakeholder Engagement DMA 2026 | L2 | 6 | 2 | 5 | 10 | 5.5 | L2 | 3 | 4 | Agent coverage insufficient for L3: need 5+ agents with 3+ categories Knowledge graph incomplete: need done_when, why, depends_on on all milestones
Product Success Agents | L1 | 8 | 8 | 5 | 7 | 7.1 | L3 | 2.2 | 5 | Agent coverage insufficient for L3: need 5+ agents with 3+ categories
Corporate Social Responsibility | L1 | 8 | 8 | 0 | 7 | 5.8 | L2 | 2.1 | 0 | No agents: need at least 2-3 agents for 90% automation Agent coverage insufficient for L3: need 5+ agents with 3+ categories
MCP Workday | L1 | 9.5 | 6 | 0 | 10 | 6.3 | L2 | 2 | 0 | No agents: need at least 2-3 agents for 90% automation Agent coverage insufficient for L3: need 5+ agents with 3+ categories
ESG Masterclass | L1 | 6 | 8 | 8 | 10 | 7.8 | L3 | 1.5 | 3 | Knowledge graph incomplete: need done_when, why, depends_on on all milestones

## BIP HR Plan
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Navigator | # | ID | Level | Area BIP | Titolo | Status | Priorita | Owner | Effort | Q1 | Q2 | Q3 | Q4 | Agenti | Note
Area 1 |  |  |  | Ecological Transition | environment, carbon-wallet, operations
operations | 1 | operations/travel-catalog | L2 | Ecological Transition | Travel catalog | In progress | H2 | Lucia Longoni | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 2 | operations/commute-catalog | L2 | Ecological Transition | Commute catalog | In progress | H1 | Lucia Longoni | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 3 | operations/environment-community | L2 | Ecological Transition | Environment Community | In progress | H2 | Alice Simonetta | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 4 | operations/prison-employment-vigevano | L2 | Ecological Transition | Prison Employment (Vigevano) | In progress | H2 | Stefania Pesola | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 5 | operations/gender-equality | L2 | Ecological Transition | Gender Equality | In progress | H1 | Stefania Pesola | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 6 | operations/social-impact-non-profit | L2 | Ecological Transition | Social Impact Non Profit | In progress | H1 | Alice Simonetta | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 7 | operations/holding-the-space-pii | L2 | Ecological Transition | Holding the space (PII) | In progress | H1 | Francesco Mondora | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 8 | operations/public-funds-bandi | L2 | Ecological Transition | Public funds / bandi | In progress | H2 | Alice Simonetta | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 9 | operations/admin-esg | L2 | Ecological Transition | Admin ESG | In progress | H2 | Lucia Longoni | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 10 | operations/ground-control-sistema-operativo-esg | L2 | Ecological Transition | Ground Control — sistema operativo ESG | In progress | H2 | Francesco Mondora | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
environment | 11 | environment/bosco-teamsystem-audit-iso-14068-2-e-pefc | L1 | Ecological Transition | Bosco TeamSystem — audit ISO 14068-2 e PEFC | In progress | H1 | Michele Romano Giamba | Medium |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 12 | environment/spritepinky-ghg-scope-3 | L1 | Ecological Transition | SpritePinky + GHG Scope 3 | In progress | H3 | Michele Romano Giamba | High |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 13 | environment/environment-policy-approvazione | L1 | Ecological Transition | Environment Policy — approvazione | In progress | H2 | Francesco Mondora | Medium |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 14 | environment/tnfd-leap-assessment | L1 | Ecological Transition | TNFD LEAP assessment | Planned | H1 | Francesco Mondora | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 15 | environment/data-capture-piattaforma-esg-operativa | L1 | Ecological Transition | Data Capture piattaforma ESG — operativa | In progress | H2 | Irene Brambilla | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 16 | environment/scope-12-split-per-subsidiary | L1 | Ecological Transition | Scope 1+2 split per subsidiary | Planned | H2 | Michele Romano Giamba | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 17 | environment/certificazione-iso-14068-1-carbon-neutrality | L1 | Ecological Transition | Certificazione ISO 14068-1 — Carbon Neutrality | Planned | H2 | Michele Romano Giamba | Medium |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 18 | environment/botanical-garden-orto-botanico-teamsystem | L1 | Ecological Transition | Botanical Garden — Orto Botanico TeamSystem | Planned | H2 | Francesco Vanossi | Medium |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 19 | environment/rendicontazione-ghg-scope-3-hf-su-novata | L1 | Ecological Transition | Rendicontazione GHG Scope 3 — H&F su Novata | In progress | H2 | Michele Romano Giamba | Low |  | x |  |  | 0 agenti — suggeriti: tracking
carbon-wallet | 20 | carbon-wallet/metodologia-avoided-emissions-validazione | L1 | Ecological Transition | Metodologia Avoided Emissions — validazione | In progress | H1 | Anna Forlati | Medium |  |  | x |  | 0 agenti — suggeriti: compliance, tracking
carbon-wallet | 21 | carbon-wallet/engine-carbonwallet-bozza-v1 | L1 | Ecological Transition | Engine CarbonWallet — bozza v1 | Planned | H3 | Anna Forlati | Medium |  |  | x |  | 0 agenti — suggeriti: compliance, tracking
carbon-wallet | 22 | carbon-wallet/engine-carbonwallet-v2-e-lancio | L1 | Ecological Transition | Engine CarbonWallet — v2 e lancio | Planned | H3 | Anna Forlati | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking
Area 2 |  |  |  | Inclusion & Social | inclusion, csr, operations
csr | 23 | csr/project-management-setup-e-validazione | L1 | Inclusion & Social | Project Management — setup e validazione | In progress | H2 | Soljane Sabre | Medium |  | x |  |  | 0 agenti — suggeriti: engagement
csr | 24 | csr/project-design-disegno-bando-e-consultazione | L1 | Inclusion & Social | Project Design — disegno bando e consultazione | In progress | H1 | Soljane Sabre | High |  |  | x |  | 0 agenti — suggeriti: engagement
csr | 25 | csr/pilot-launch-call-selezione-e-onboarding-ets | L1 | Inclusion & Social | Pilot Launch — call, selezione e onboarding ETS | Planned | H1 | Soljane Sabre | Medium |  |  |  | x | 0 agenti — suggeriti: engagement
inclusion | 26 | inclusion/policy-inclusione-pubblicazione | L1 | Inclusion & Social | Policy Inclusione — pubblicazione | In progress | H3 | Stefania Pesola | Medium |  | x |  |  | 0 agenti — suggeriti: engagement
inclusion | 27 | inclusion/inclusion-index-somministrazione-e-elaborazione | L1 | Inclusion & Social | Inclusion Index — somministrazione e elaborazione | Planned | H3 | Stefania Pesola | Medium |  |  | x |  | 0 agenti — suggeriti: engagement
inclusion | 28 | inclusion/masterclass-inclusione-fnc-erogazione | L1 | Inclusion & Social | Masterclass Inclusione FNC — erogazione | Planned | H3 | Stefania Pesola | Low |  |  |  | x | 0 agenti — suggeriti: engagement
operations | 29 | operations/travel-catalog | L2 | Inclusion & Social | Travel catalog | In progress | H2 | Lucia Longoni | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 30 | operations/commute-catalog | L2 | Inclusion & Social | Commute catalog | In progress | H1 | Lucia Longoni | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 31 | operations/environment-community | L2 | Inclusion & Social | Environment Community | In progress | H2 | Alice Simonetta | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 32 | operations/prison-employment-vigevano | L2 | Inclusion & Social | Prison Employment (Vigevano) | In progress | H2 | Stefania Pesola | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 33 | operations/gender-equality | L2 | Inclusion & Social | Gender Equality | In progress | H1 | Stefania Pesola | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 34 | operations/social-impact-non-profit | L2 | Inclusion & Social | Social Impact Non Profit | In progress | H1 | Alice Simonetta | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 35 | operations/holding-the-space-pii | L2 | Inclusion & Social | Holding the space (PII) | In progress | H1 | Francesco Mondora | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 36 | operations/public-funds-bandi | L2 | Inclusion & Social | Public funds / bandi | In progress | H2 | Alice Simonetta | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 37 | operations/admin-esg | L2 | Inclusion & Social | Admin ESG | In progress | H2 | Lucia Longoni | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
operations | 38 | operations/ground-control-sistema-operativo-esg | L2 | Inclusion & Social | Ground Control — sistema operativo ESG | In progress | H2 | Francesco Mondora | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking, engagement
Area 3 |  |  |  | Contribution & Nature | environment
environment | 39 | environment/bosco-teamsystem-audit-iso-14068-2-e-pefc | L1 | Contribution & Nature | Bosco TeamSystem — audit ISO 14068-2 e PEFC | In progress | H1 | Michele Romano Giamba | Medium |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 40 | environment/spritepinky-ghg-scope-3 | L1 | Contribution & Nature | SpritePinky + GHG Scope 3 | In progress | H3 | Michele Romano Giamba | High |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 41 | environment/environment-policy-approvazione | L1 | Contribution & Nature | Environment Policy — approvazione | In progress | H2 | Francesco Mondora | Medium |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 42 | environment/tnfd-leap-assessment | L1 | Contribution & Nature | TNFD LEAP assessment | Planned | H1 | Francesco Mondora | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 43 | environment/data-capture-piattaforma-esg-operativa | L1 | Contribution & Nature | Data Capture piattaforma ESG — operativa | In progress | H2 | Irene Brambilla | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 44 | environment/scope-12-split-per-subsidiary | L1 | Contribution & Nature | Scope 1+2 split per subsidiary | Planned | H2 | Michele Romano Giamba | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 45 | environment/certificazione-iso-14068-1-carbon-neutrality | L1 | Contribution & Nature | Certificazione ISO 14068-1 — Carbon Neutrality | Planned | H2 | Michele Romano Giamba | Medium |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 46 | environment/botanical-garden-orto-botanico-teamsystem | L1 | Contribution & Nature | Botanical Garden — Orto Botanico TeamSystem | Planned | H2 | Francesco Vanossi | Medium |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 47 | environment/rendicontazione-ghg-scope-3-hf-su-novata | L1 | Contribution & Nature | Rendicontazione GHG Scope 3 — H&F su Novata | In progress | H2 | Michele Romano Giamba | Low |  | x |  |  | 0 agenti — suggeriti: tracking
Area 4 |  |  |  | Purpose & Digital | taxonomy, carbon-wallet, masterclass, ts-impact-platform
ts-impact-platform | 48 | ts-impact-platform/data-capture-modulo-operativo | L2 | Purpose & Digital | Data Capture — modulo operativo | In progress | H2 | Irene Brambilla | Low |  | x |  |  | 0 agenti — suggeriti: compliance
ts-impact-platform | 49 | ts-impact-platform/fix-debito-tecnico-migrazione-postgrespgvector | L2 | Purpose & Digital | Fix debito tecnico + migrazione Postgres/pgvector | Planned | H1 | Irene Brambilla | Low |  |  | x |  | 0 agenti — suggeriti: compliance
ts-impact-platform | 50 | ts-impact-platform/formazione-data-capture-data-owners | L2 | Purpose & Digital | Formazione Data Capture + data owners | Planned | H2 | Irene Brambilla | Low |  |  | x |  | 0 agenti — suggeriti: compliance
ts-impact-platform | 51 | ts-impact-platform/integrazione-workday-via-api | L2 | Purpose & Digital | Integrazione Workday via API | Planned | H2 | Irene Brambilla | Low |  |  | x |  | 0 agenti — suggeriti: compliance
ts-impact-platform | 52 | ts-impact-platform/refactor-su-1platform | L2 | Purpose & Digital | Refactor su 1Platform | Planned | H2 | Irene Brambilla | Low |  |  |  | x | 0 agenti — suggeriti: compliance
ts-impact-platform | 53 | ts-impact-platform/kpi-e-targets-in-piattaforma | L2 | Purpose & Digital | KPI e Targets in piattaforma | Planned | H2 | Irene Brambilla | Low |  |  |  | x | 0 agenti — suggeriti: compliance
ts-impact-platform | 54 | ts-impact-platform/dma-ma-doppia-materialita-acquisizioni | L2 | Purpose & Digital | DMA M&A — doppia materialita acquisizioni | Planned | H2 | Irene Brambilla | Low |  |  |  | x | 0 agenti — suggeriti: compliance
masterclass | 55 | masterclass/preparazione-masterclass | L1 | Purpose & Digital | Preparazione masterclass | In progress | H3 | Francesco Mondora | Medium |  |  | x |  | 3 agenti
masterclass | 56 | masterclass/mcp-esg-per-dipendenti | L1 | Purpose & Digital | MCP ESG per dipendenti | In progress | H3 | Francesco Mondora | Low |  |  | x |  | 3 agenti
masterclass | 57 | masterclass/erogazione | L1 | Purpose & Digital | Erogazione | Planned | H2 | Francesco Mondora | Low |  |  | x |  | 3 agenti
taxonomy | 58 | taxonomy/mappatura-nace-prodotti-candidati | L1 | Purpose & Digital | Mappatura NACE prodotti candidati | Completed | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
taxonomy | 59 | taxonomy/classificazione-prodotti-con-product-success | L1 | Purpose & Digital | Classificazione prodotti con Product Success | Completed | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
taxonomy | 60 | taxonomy/dati-finanziari-per-prodotto | L1 | Purpose & Digital | Dati finanziari per prodotto | In progress | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
taxonomy | 61 | taxonomy/agenti-esg-embedded-in-product-success | L1 | Purpose & Digital | Agenti ESG embedded in Product Success | Planned | H3 | Anna Forlati | Medium |  |  | x |  | 6 agenti
taxonomy | 62 | taxonomy/dnsh-check-per-prodotto | L1 | Purpose & Digital | DNSH check per prodotto | Blocked | H1 | Anna Forlati | Low |  |  | x |  | 6 agenti
taxonomy | 63 | taxonomy/validazione-board | L1 | Purpose & Digital | Validazione Board | Planned | H2 | Francesco Mondora | Low |  |  | x |  | 6 agenti
taxonomy | 64 | taxonomy/social-taxonomy-alignment | L1 | Purpose & Digital | Social Taxonomy alignment | Planned | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
carbon-wallet | 65 | carbon-wallet/metodologia-avoided-emissions-validazione | L1 | Purpose & Digital | Metodologia Avoided Emissions — validazione | In progress | H1 | Anna Forlati | Medium |  |  | x |  | 0 agenti — suggeriti: compliance, tracking
carbon-wallet | 66 | carbon-wallet/engine-carbonwallet-bozza-v1 | L1 | Purpose & Digital | Engine CarbonWallet — bozza v1 | Planned | H3 | Anna Forlati | Medium |  |  | x |  | 0 agenti — suggeriti: compliance, tracking
carbon-wallet | 67 | carbon-wallet/engine-carbonwallet-v2-e-lancio | L1 | Purpose & Digital | Engine CarbonWallet — v2 e lancio | Planned | H3 | Anna Forlati | Low |  |  |  | x | 0 agenti — suggeriti: compliance, tracking
Area 5 |  |  |  | Governance & Compliance | reporting, suppliers
reporting | 68 | reporting/nfd-2025 | L2 | Governance & Compliance | NFD 2025 | In progress | H1 | Lucia Longoni | Medium |  |  | x |  | 11 agenti
reporting | 69 | reporting/ri-2025 | L2 | Governance & Compliance | RI 2025 | In progress | H1 | Lucia Longoni | Medium |  |  | x |  | 11 agenti
reporting | 70 | reporting/r1-standards-kpi | L2 | Governance & Compliance | R1 Standards & KPI | In progress | H1 | Lucia Longoni | Low |  | x |  |  | 11 agenti
reporting | 71 | reporting/rating-esg-novata-ecovadis | L2 | Governance & Compliance | Rating ESG — Novata & Ecovadis | In progress | H2 | Lucia Longoni | Low |  |  | x |  | 11 agenti
reporting | 72 | reporting/deloitte-limited-assurance | L2 | Governance & Compliance | Deloitte limited assurance | Planned | H1 | Francesco Mondora | Low |  |  |  | x | 11 agenti
suppliers | 73 | suppliers/piattaforma-supplier-valutazione-trasparenza | L2 | Governance & Compliance | Piattaforma Supplier — Valutazione & Trasparenza | In progress | H1 | Lucia Longoni | Medium |  |  | x |  | 0 agenti — suggeriti: compliance, engagement
suppliers | 74 | suppliers/piattaforma-supplier-modulo-stakeholder-engagement | L2 | Governance & Compliance | Piattaforma Supplier — Modulo Stakeholder Engagement | Planned | H2 | Lucia Longoni | Low |  |  |  | x | 0 agenti — suggeriti: compliance, engagement
suppliers | 75 | suppliers/top-10-supplier-interviews | L2 | Governance & Compliance | Top 10 supplier interviews | Planned | H2 | Lucia Longoni | Medium |  |  | x |  | 0 agenti — suggeriti: compliance, engagement
suppliers | 76 | suppliers/supplier-code-of-conduct-csddd-ready | L2 | Governance & Compliance | Supplier Code of Conduct — CSDDD ready | Planned | H1 | Lucia Longoni | Medium |  |  |  | x | 0 agenti — suggeriti: compliance, engagement
suppliers | 77 | suppliers/client-survey-s4 | L2 | Governance & Compliance | Client survey S4 | Planned | H1 | Lucia Longoni | Low |  |  | x |  | 0 agenti — suggeriti: compliance, engagement
suppliers | 78 | suppliers/supplier-inclusion-green-procurement | L2 | Governance & Compliance | Supplier Inclusion (green procurement) | Planned | H2 | Lucia Longoni | Low |  |  | x |  | 0 agenti — suggeriti: compliance, engagement
Area 6 |  |  |  | Transparency & Engagement | stakeholder-engagement, reporting
reporting | 79 | reporting/nfd-2025 | L2 | Transparency & Engagement | NFD 2025 | In progress | H1 | Lucia Longoni | Medium |  |  | x |  | 11 agenti
reporting | 80 | reporting/ri-2025 | L2 | Transparency & Engagement | RI 2025 | In progress | H1 | Lucia Longoni | Medium |  |  | x |  | 11 agenti
reporting | 81 | reporting/r1-standards-kpi | L2 | Transparency & Engagement | R1 Standards & KPI | In progress | H1 | Lucia Longoni | Low |  | x |  |  | 11 agenti
reporting | 82 | reporting/rating-esg-novata-ecovadis | L2 | Transparency & Engagement | Rating ESG — Novata & Ecovadis | In progress | H2 | Lucia Longoni | Low |  |  | x |  | 11 agenti
reporting | 83 | reporting/deloitte-limited-assurance | L2 | Transparency & Engagement | Deloitte limited assurance | Planned | H1 | Francesco Mondora | Low |  |  |  | x | 11 agenti
stakeholder-engagement | 84 | stakeholder-engagement/open-doors-s1-stakeholder-engagement-campaign | L2 | Transparency & Engagement | Open Doors — S1 stakeholder engagement campaign | In progress | H2 | Alice Simonetta | Low |  |  | x |  | 4 agenti
stakeholder-engagement | 85 | stakeholder-engagement/local-communities-s3 | L2 | Transparency & Engagement | Local communities S3 | In progress | H2 | Alice Simonetta | Low |  |  | x |  | 4 agenti
stakeholder-engagement | 86 | stakeholder-engagement/engagement-agentico-dipendenti | L2 | Transparency & Engagement | Engagement agentico dipendenti | In progress | H3 | Francesco Mondora | Low |  |  | x |  | 4 agenti
stakeholder-engagement | 87 | stakeholder-engagement/sergenti-sistema-agentico-esg-team | L2 | Transparency & Engagement | Sergenti — sistema agentico ESG team | In progress | H3 | Francesco Mondora | Low |  |  | x |  | 4 agenti
stakeholder-engagement | 88 | stakeholder-engagement/impact-report-as-engagement-instrument | L2 | Transparency & Engagement | Impact Report as engagement instrument | In progress | H2 | Francesco Mondora | Low |  |  | x |  | 4 agenti
stakeholder-engagement | 89 | stakeholder-engagement/sbm-2-disclosure-draft | L2 | Transparency & Engagement | SBM-2 disclosure draft | Planned | H1 | Irene Brambilla | Low |  |  |  | x | 4 agenti
Area 7 |  |  |  | Overboard | taxonomy, environment, techconference
taxonomy | 90 | taxonomy/mappatura-nace-prodotti-candidati | L1 | Overboard | Mappatura NACE prodotti candidati | Completed | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
taxonomy | 91 | taxonomy/classificazione-prodotti-con-product-success | L1 | Overboard | Classificazione prodotti con Product Success | Completed | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
taxonomy | 92 | taxonomy/dati-finanziari-per-prodotto | L1 | Overboard | Dati finanziari per prodotto | In progress | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
taxonomy | 93 | taxonomy/agenti-esg-embedded-in-product-success | L1 | Overboard | Agenti ESG embedded in Product Success | Planned | H3 | Anna Forlati | Medium |  |  | x |  | 6 agenti
taxonomy | 94 | taxonomy/dnsh-check-per-prodotto | L1 | Overboard | DNSH check per prodotto | Blocked | H1 | Anna Forlati | Low |  |  | x |  | 6 agenti
taxonomy | 95 | taxonomy/validazione-board | L1 | Overboard | Validazione Board | Planned | H2 | Francesco Mondora | Low |  |  | x |  | 6 agenti
taxonomy | 96 | taxonomy/social-taxonomy-alignment | L1 | Overboard | Social Taxonomy alignment | Planned | H1 | Anna Forlati | Low |  | x |  |  | 6 agenti
environment | 97 | environment/bosco-teamsystem-audit-iso-14068-2-e-pefc | L1 | Overboard | Bosco TeamSystem — audit ISO 14068-2 e PEFC | In progress | H1 | Michele Romano Giamba | Medium |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 98 | environment/spritepinky-ghg-scope-3 | L1 | Overboard | SpritePinky + GHG Scope 3 | In progress | H3 | Michele Romano Giamba | High |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 99 | environment/environment-policy-approvazione | L1 | Overboard | Environment Policy — approvazione | In progress | H2 | Francesco Mondora | Medium |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 100 | environment/tnfd-leap-assessment | L1 | Overboard | TNFD LEAP assessment | Planned | H1 | Francesco Mondora | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 101 | environment/data-capture-piattaforma-esg-operativa | L1 | Overboard | Data Capture piattaforma ESG — operativa | In progress | H2 | Irene Brambilla | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 102 | environment/scope-12-split-per-subsidiary | L1 | Overboard | Scope 1+2 split per subsidiary | Planned | H2 | Michele Romano Giamba | Low |  |  | x |  | 0 agenti — suggeriti: tracking
environment | 103 | environment/certificazione-iso-14068-1-carbon-neutrality | L1 | Overboard | Certificazione ISO 14068-1 — Carbon Neutrality | Planned | H2 | Michele Romano Giamba | Medium |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 104 | environment/botanical-garden-orto-botanico-teamsystem | L1 | Overboard | Botanical Garden — Orto Botanico TeamSystem | Planned | H2 | Francesco Vanossi | Medium |  |  |  | x | 0 agenti — suggeriti: tracking
environment | 105 | environment/rendicontazione-ghg-scope-3-hf-su-novata | L1 | Overboard | Rendicontazione GHG Scope 3 — H&F su Novata | In progress | H2 | Michele Romano Giamba | Low |  | x |  |  | 0 agenti — suggeriti: tracking

## Budget
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Stream | Milestone | Voce | Vendor | Importo | Valuta | Owner | N. RDA | Stato RDA | Approvato da | Data RDA | Scadenza | Note
program | RI 2025 — pubblicazione Relazione d'Impatto | Agentizzazione rendering Relazione d'Impatto | Cristina del Re | 10000 | EUR | Lucia Longoni | RDA-2026-028 | paid | Donatella Isaia | 2026-05-10 |  | rendering automatizzato RI via agenti
program | RI 2025 — pubblicazione Relazione d'Impatto | Agentizzazione rendering NFD — fase 2 | Cristina del Re | 5000 | EUR | Lucia Longoni | RDA-2026-060 | requested |  | 2026-06-20 | 2026-07-31 | completamento NFD luglio
program | RI 2025 — pubblicazione Relazione d'Impatto | Piattaforma Ecovadis — licenza | Ecovadis | 2500 | EUR | Lucia Longoni | RDA-2026-031 | paid |  | 2026-05-15
program | Carbon Emission Strategy + Environment Policy | Gestione forestale Bosco TeamSystem — interventi luglio | Garbaccio | 50000 | EUR | Francesco Mondora |  | draft |  |  | 2026-07-31 | interventi forestali estate 2026
program | Carbon Emission Strategy + Environment Policy | Gestione forestale Bosco TeamSystem — interventi ottobre | Garbaccio | 50000 | EUR | Francesco Mondora |  | draft |  |  | 2026-10-31 | interventi forestali autunno 2026
|  | TOTALE |  | 117500

## Weekly Notes
AUTO-GENERATED by Ground Control (viz/build.py). Do not edit manually — changes will be overwritten on the next generation. Data source: ground-control.yaml / ground-control.md files across repo submodules. Generato il 29/06/2026 alle 18:43
Settimana | Data | Autore | Testo
W25 | 16-22 giugno 2026 | Lucia | RI quasi chiusa, manca solo impaginazione finale. Cristina del Re consegna il rendering entro venerdi.
W25 | 16-22 giugno 2026 | Francesco | incontro con Anna su Taxonomy, deciso di rimandare la presentazione Board a settembre perche mancano i dati CarbonWallet. Rischio: se CarbonWallet non ha i dati entro agosto, il Board slitta. Preparazione per evento H&F del 24 giugno, Francesco speaker.
W25 | 16-22 giugno 2026 | Michele | rendicontazione GHG Scope 3 per H&F su Novata in corso, coordinamento con Lucia per completare entro fine giugno.
W25 | 16-22 giugno 2026 | Stefania | policy inclusione al 60%, in attesa feedback da Marco Bertoni.